## Mk. II
		00:37:51

Test	Date	Test Duration	Running Time	Purpose	Results	Details	YouTube Video
1	2016-09-06	00:01:53	00:01:53	First Mk. II run, check out hardware	Success, Main pulley came loose	Project Log	https://www.youtube.com/watch?v=ZzuZMFTv0l8
2	2016-09-07	00:01:24	00:03:17	Hover Attempt	Partial hover, center of gravity off	Project Log	https://www.youtube.com/watch?v=ZzuZMFTv0l8
3	2016-09-07	00:02:10	00:05:27	Hover Attempt	Success, Hover	Project Log	https://www.youtube.com/watch?v=ZzuZMFTv0l8
4A	2016-09-30	00:01:40	00:07:07	Checkout, Warmup	Success
4B	2016-09-30	00:01:19	00:08:26	Hover Attempt	Partial hover, starboard doesn't lift
4C	2016-09-30	00:01:19	00:09:45	Hover Attempt with 10 lb Weight to offset cg	Partial hover, front doesn't lift
4D	2016-09-30	00:00:58	00:10:43	Hover Attempt with 10 lb Weight to offset cg	Partial hover, bucks front to back
4E	2016-09-30	00:01:26	00:12:09	Hover Attempt	Partial hover with looser lines, moves wildly back and forth. Later found that the port exhaust came loose.
5A	2016-10-02	00:02:21	00:14:30	Testing New Al Tensioner Pulley	Success, found the port exhaust was loose.
5B	2016-10-06	00:03:27	00:17:57	Testing New Al Tensioner Pulley, Hover Attempt	Success, Hovered for 25s, port exhaust came loose.
6	2016-11-04	00:04:42	00:22:39	Testing Final Al Pulleys	Success, port exhaust bolts come completely undone. Temp avionics tray comes loose.
7	2016-11-06	00:00:59	00:23:38	Testing Exhaust Repairs	Success
8	2016-11-11	00:03:57	00:27:35	Testing New Avionics Tray, Hover Attempt	Success, Partial hover, starboard doesn't lift
9	2016-11-13	00:03:35	00:31:10	Testing Pixhawk	Pixhawk lost Power On start-up. Battery having issues.
10A	2016-11-17		00:31:10	Testing Pixhawk	Solenoid Fails
10B	2016-11-13	00:02:16	00:33:26	Testing Pixhawk	Success, Recorded Pixhawk data
11	2016-11-19	00:02:28	00:35:54	Testing Pixhawk, Hover Attempt	Recorded Pixhawk data, Partial hover, starboard side won't lift
12	2016-11-20	00:01:57	00:37:51	Testing Rotor Aerodynamics with Tufts	Success, Partial hover, starboard side won't lift

## Mk. I
		00:03:59

Test	Date	Test Duration	Running Time	Purpose	Results	Details	YouTube Video
1	2014-08-29	00:00:06	00:00:06	Run on Starter Only to Check out Hardware	Success	Project Log	https://www.youtube.com/watch?v=XSjYH7lru0w
2	2014-09-01	00:00:06	00:00:12	Run on Gas for the first time	Loss of Tension, Broken Parts	Project Log	https://www.youtube.com/watch?v=mCfh3zFHTus
3	2014-10-06	00:00:05	00:00:17	Run on Starter Only to Check New Tensioner	Success	Project Log	https://www.youtube.com/watch?v=ZJ6dnGEMr3Q
4	2014-10-08	00:00:08	00:00:25	Run on Starter Only to Check Belt Guards	Success	Project Log	https://www.youtube.com/watch?v=k4okZdfEIZs
5	2014-10-11	00:00:23	00:00:48	Run on Gas for the first time, single sided belt	Success	Project Log	https://www.youtube.com/watch?v=Xh04DMtYJIM
6	2014-10-13	00:00:38	00:01:26	Run on Gas with both belts	Success	Project Log	https://www.youtube.com/watch?v=CThhOUNxjRo
7	2014-10-13	00:01:02	00:02:28	Run on Gas with both belts	Success	Project Log	https://www.youtube.com/watch?v=5GBx1uHGSno
8	2014-10-16	00:01:31	00:03:59	Run on Gas with both belts	Success	Project Log	https://www.youtube.com/watch?v=s_NvtabTg0I
9	2014-11-15		00:03:59	Checking out Test Stand	Success	Project Log	https://www.youtube.com/watch?v=KvBA0cagbM8
10				Checking out Test Stand	Success	Project Log	https://www.youtube.com/watch?v=KvBA0cagbM8